## Sheet1
Legend:
| Project Start Date: |  | 2021-03-22 |  |  |  | On Track |  |  |  | Low Risk |  |  |  | Med Risk |  |  |  | High Risk
Gantt Chart
[6 empty] | March | [6 empty] | April
[6 empty] | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
[6 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5
Milestone Description | Category | Assigned To | Progress | Start | No. Days | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F
Establish Front/Back End | On Track | Steven | 100% | 2021-03-25 | 2 | bar: Week 1 M to Week 1 T
Learn Git | On Track | Steven | 100% | 2021-04-14 | 3 | bar: Week 1 M to Week 1 T; Week 3 S to Week 4 T
Review React and other Tech | On Track | Steven | 100% | 2021-03-27 | 11 | bar: Week 1 W to Week 1 S; Week 2 M to Week 2 S
Connect and implement API | On Track | Steven | 100% | 2021-04-03 | 8 | bar: Week 2 W to Week 2 F; Week 5 M to Week 5 F
Create Visualizations | On Track | Steven | 100% | 2021-04-15 | 6 | bar: Week 4 M to Week 4 S
Integrate Material UI/Designs | On Track | Steven | 90% | 2021-04-08 | 10 | bar: Week 3 M to Week 3 S; Week 4 M to Week 4 T
Deploy application | Low Risk | Steven | 100% | 2021-04-27 | 2 | bar: Week 5 T to Week 5 F
Paper and forms | Low Risk | Steven | 100% | 2021-04-23 | 4 | bar: Week 5 T to Week 5 F
Code Features | Med Risk | Steven | 80% | 2021-04-12 | 15 | bar: Week 3 F to Week 5 F